## Master
USER STORY: 1
Task | Time | Notes
Login Page in HTML | 1hr
Integrate OAuth to authenticate user | 2h
Error page for failed auth | 1hr
Score display page | 1h
Write API access calls to Reddit | 4h | Includes Research time
Store info retrieved from reddit | 1hr
Write API access calls to OpenAI | 2h
Store info retrieved from OpenAI | 1hr
Calculate scoring using info retrieved from OpenAI | 1h
Create Tables to Display Categories and Percentages from Open AI | 1hr
Create log out feature | 1hr
Total: 16 hrs

## Aaron
Task | Time | Notes
Login Page in HTML | 30m
Integrate OAuth to authenticate user | 2h
Error page for failed auth | 30m
Score display page | 1h
Write API access calls to Reddit | 4h | Not sure how the API works-time includes research needed
Store info retrieved from reddit | 30m
Write API access calls to OpenAI | 2h
Store info retrieved from OpenAI | 30m
Calculate scoring using info retrieved from OpenAI | 1h
Display the computed score | 30m
12h 30m
This is based on user story 1, which does not contain database access or anything beyond basic functionality

## Rithvik
Task | Time to Complete
Create UI for website | 2hr
Log-in using Reddit API | 2hr
Gathering user information from reddit | 2hr
Setting up OpenAI API | 1hr
Send API Calls to OpenAI API | 1hr
Retrieve Data from OpenAI API | 1hr
Use OpenAI API and translate that information to scores | 2hr
Use OpenAI API data to also gather and store categories and percentages | 1hr
Create Tables in Website to Display Data | 1hr
Total: 13hrs

## Jason
Task | Time
Login Page in HTML | 1hr
Login with Reddit API | 30 min
Retrieve User information | 15 min
Query user information | 30 min
Openai API calls | 30 min
Retrieve OpenAI information | 30 min
Store in Database | 15 min
Calculate Score | 30 min
Convert Score to category | 1:30 min
Display on website | 1:30 min